## Sheet1
Week 0 | 2012-08-27 | 2012-08-31 | Week 6 | 2012-10-08 | 2012-10-10
| Kickoff meeting |  |  | Requirements Definition
| Requirements Definition |  |  | Architecture Development
Week 1 | 2012-09-03 | 2012-09-07 |  | OSMDroid Demo
| Requirements Definition |  |  | Android Local Network Demo
| Architecture Development |  |  | System Requirements Review
Week 2 | 2012-09-10 | 2012-09-14 |  | Senior Project Presentations
| Requirements Definition |  | Week 7 | 2012-10-15 | 2012-10-19
| Architecture Development |  |  | Preliminary Design Development
Week 3 | 2012-09-17 | 2012-09-21 |  | Environment Setup
| Requirements Definition |  |  | Use Cases
| Architecture Development |  | Week 8 | 2012-10-22 | 2012-10-26
| Raytheon Site Visit |  |  | Preliminary Design Development
Week 4 | 2012-09-24 | 2012-09-28 |  | Environment Setup
| Requirements Definition |  |  | Use Cases
| Architecture Development |  | Week 9 | 2012-10-29 | 2012-11-02
| OSMDroid Demo |  |  | Sprint Establishment
| Android Local Network Demo |  |  | Guided Coding
Week 5 | 2012-10-01 | 2012-10-05 |  | Use Cases
| Requirements Definition |  | Week 10 | 2012-11-05 | 2012-11-09
| Architecture Development |  |  | Coding
| OSMDroid Demo |  |  | Use Cases
Android Local Network Demo
Key
Activity
Sofware
Documentation